## Remediation Roadmap
RegTech Solutions — Compliance Remediation Roadmap
Treatment plans for each compliance gap with owner, due date, and current status
Treatment ID | Linked Gap | Type | Owner | Due Date | Status | Treatment Plan
TRT-mna4lcvo | No formal PCI DSS v4.0 gap assessment completed since version upgrade | Mitigate | Compliance Architect | 2026-03-16 | In Progress | Qualified assessor engaged for PCI DSS v4.0 gap assessment. New requirements being mapped against existing controls. Remediation roadmap created before next client audit cycle.
TRT-mna4mefj | HIPAA Business Associate Agreements missing for 3 active healthcare client integrations | Mitigate | Compliance Architect | 2026-03-17 | In Progress | Legal drafting BAAs for all 3 healthcare clients immediately. PHI processing suspended without signed BAA. BAA register updated and reviewed quarterly.
TRT-mna4n4g7 | No documented process for handling simultaneous audit requests across PCI DSS, SOC 2, and HIPAA | Mitigate | Compliance Architect | 2026-03-19 | Planned | Unified audit response process being documented across all three frameworks. Single point of contact assigned per audit. Evidence request templates created for each framework.
TRT-mna4npsj | Control crosswalk not documented across PCI DSS, SOC 2, and HIPAA frameworks | Mitigate | Compliance Architect | 2026-03-18 | Planned | Control crosswalk mapping all 15 controls across PCI DSS, SOC 2, and HIPAA being built. Where one control covers multiple frameworks documented. Used during audits to reduce duplication.
TRT-mna4o8j9 | Penetration testing not conducted against healthcare and financial client data environments | Mitigate | Security Lead | 2026-03-19 | Planned | Qualified pen testing firm engaged to test all PHI and financial client systems. Internal and external testing per PCI DSS Req 11.3. Critical findings remediated within 30 days.