## Treatment Plan
TechStart Inc — Risk Treatment Plan
Treatment ID | Linked Risk | Treatment Type | Owner | Due Date | Status | Treatment Plan
TRT-mn36zewj | External attacker exploits weak MFA causing unauthorized access to customer database | Mitigate | Security Lead | 2026-03-05 | Completed | Enable MFA on all admin AWS accounts. IAM policies updated to block console access without MFA. Security lead verifying before go-live.
TRT-mn370awg | Internal misconfiguration exploits unsecured S3 bucket causing customer data exposed to public internet | Mitigate | DevOps Lead | 2026-03-05 | Completed | S3 Block Public Access enabled at account level. AWS Config rule set up. DevOps doing full bucket audit before migration completes.
TRT-mn375gzr | Threat actor exploits unencrypted data in transit causing interception of customer PII during migration | Mitigate | Security Lead | 2026-03-05 | Planned | All migration scripts reviewed for TLS 1.2. Network logs checked to confirm no unencrypted paths before data movement starts.
TRT-mn376akd | Employee endpoint exploits phishing email causing credential compromise and lateral movement into AWS | Mitigate | HR Team | 2026-03-06 | Planned | Phishing training scheduled for all staff. IT running simulated campaign after training. Staff who fail get immediate follow-up session.
TRT-mn376y0i | Third-party vendor exploits inadequate security assessment causing supply chain breach into AWS environment | Mitigate | GRC Manager | 2026-03-06 | Planned | Security questionnaire sent to all active vendors. New vendors blocked until assessment done. Annual review added to GRC calendar.