## CIS Audit Findings
CloudNative Corp — CIS AWS Benchmark Audit Findings
Misconfigurations and findings from AWS security assessment with remediation recommendations
Finding ID | Title | Severity | Status | Owner | Due Date | Description | Recommendation
FND-mn8qkwzt | S3 buckets with public access enabled exposing enterprise client data | Critical | In Progress | DevOps Lead | 2026-03-14 | Audit found multiple S3 buckets with public access enabled. Client data accessible to anyone on the internet without authentication. | Enable S3 Block Public Access at account level. Set up AWS Config rule to detect and alert on any public bucket. Audit all existing buckets and restrict permissions.
FND-mn8qlt4p | IAM policies granting excessive privileges violating least privilege principle | Critical | In Progress | Cloud Security Engineer | 2026-03-14 | IAM users and roles have wildcard permissions allowing unrestricted access across all AWS services. Several developer accounts have admin-level access not required for their role. | Review and scope all IAM policies to least privilege. Replace wildcard permissions with specific resource-level policies. Implement AWS IAM Access Analyzer to flag overly permissive policies.
FND-mn8qmo4w | CloudTrail logging disabled in multiple AWS regions | High | Open | Cloud Security Engineer | 2026-03-15 | CloudTrail not enabled in all regions. Activity in unlogged regions goes undetected. Any unauthorised access or config changes leave no audit trail. | Enable CloudTrail in all regions including global services. Ship logs to centralised S3 bucket with restricted access. Enable log file integrity validation.
FND-mn8qndzt | Security groups allowing unrestricted inbound access on sensitive ports | High | Open | Cloud Security Engineer | 2026-03-15 | Several EC2 security groups allow inbound traffic from 0.0.0.0/0 on ports 22 (SSH) and 3389 (RDP). Exposes production servers directly to the internet. | Remove all inbound rules allowing unrestricted SSH and RDP access. Restrict to specific IP ranges or route through bastion host. Review all security groups against CIS AWS Benchmark.
FND-mn8qo752 | MFA not enforced on IAM user accounts including privileged users | High | Open | Cloud Security Engineer | 2026-03-15 | Multiple IAM user accounts including admin accounts operating without MFA. A compromised password alone is enough to access all 50+ client environments. | Enforce MFA on all IAM users through IAM policy. Block console access for accounts without MFA. Prioritise privileged and admin accounts immediately.