## Risk Register
TechStart Inc — Risk Register
Framework: ISO 27001 ¦ Scope: Cloud migration to AWS
Risk ID | Risk Title | Category | Owner | Likelihood (1-5) | Impact (1-5) | Risk Score | Severity | Status | Description | Rationale | Treatment
RSK-mn35y0qr | External attacker exploits weak MFA causing unauthorized access to customer database | Access Control | Security Lead | 4 | 5 | 20 | Critical | Open | Admin accounts on AWS lack strong MFA. One compromised password gives direct access to 5M+ customer records. | Likelihood 4 — teams skip MFA during fast migrations. Impact severe — PII breach means GDPR fines and client loss. | Mitigate: Enable MFA on all admin AWS accounts. IAM policies updated to block console access without MFA. Security lead verifying before go-live.
RSK-mn35z5pm | Internal misconfiguration exploits unsecured S3 bucket causing customer data exposed to public internet | Application Security | DevOps Lead | 4 | 4 | 16 | High | Open | S3 buckets misconfigured as public during migration. No hacker needed — wrong setting exposes everything. | Likelihood 4 — multiple people provisioning quickly means mistakes happen. Impact major — public S3 triggers GDPR directly. | Mitigate: S3 Block Public Access enabled at account level. AWS Config rule set up. DevOps doing full bucket audit before migration completes.
RSK-mn3617rf | Employee endpoint exploits phishing email causing credential compromise and lateral movement into AWS | Human Error | IT Operations | 4 | 4 | 16 | High | Open | DevOps team accesses AWS from laptops. One phishing click gives attacker elevated cloud access. | Likelihood 4 — phishing targets companies during infrastructure changes. Impact major — elevated migration permissions mean wider damage. | Mitigate: Phishing training scheduled for all staff. IT running simulated campaign after training. Staff who fail get immediate follow-up session.
RSK-mn36034v | Threat actor exploits unencrypted data in transit causing interception of customer PII during migration | Data Protection | Security Lead | 3 | 4 | 12 | Medium | Open | Migration scripts moving data without TLS enforcement. Legacy configs often miss this. | Likelihood 3 — possible when old scripts are reused. Impact major — 72-hour GDPR breach notification required. | Mitigate: All migration scripts reviewed for TLS 1.2. Network logs checked to confirm no unencrypted paths before data movement starts.
RSK-mn362geh | Third-party vendor exploits inadequate security assessment causing supply chain breach into AWS environment | Vendor Risk | GRC Manager | 3 | 4 | 12 | Medium | Open | Vendors onboarded without security review. Compromised vendor API key gives silent access through trusted connection. | Likelihood 3 — assessment skipped during fast onboarding. Impact major — supply chain attacks go undetected for weeks. | Mitigate: Security questionnaire sent to all active vendors. New vendors blocked until assessment done. Annual review added to GRC calendar.