## BC Risk Register
CriticalOps Inc — Business Continuity Risk Register
Frameworks: ISO 27001, COBIT, ISO 22301 ¦ Critical infrastructure resilience for water and power systems
Risk ID | Risk Title | Category | Owner | Likelihood (1-5) | Impact (1-5) | Risk Score | Severity | Status | Description | Rationale
RSK-mna2vzgp | Ransomware attack exploits unpatched SCADA systems causing extended operational shutdown affecting 10M+ citizens | Application Security | Operations Manager | 4 | 5 | 20 | Critical | Open | SCADA systems controlling water treatment and power grid are prime ransomware targets. Extended shutdown means 10M+ citizens lose access to clean water or electricity. | Likelihood 4 ransomware attacks on critical infrastructure increasing globally. Impact severe any SCADA downtime beyond RTO endangers public safety and triggers CISA mandatory reporting.
RSK-mna2wubi | Natural disaster exploits single-site dependency causing complete loss of SCADA operations with no failover | Availability | Business Continuity Manager | 3 | 5 | 15 | High | Open | If primary facility is hit by flood or fire and DR site isn't maintained, there's no fallback. Operations go completely dark with no way to control water treatment or power grid remotely. | Likelihood 3 — natural disasters are inevitable over time. Impact severe complete loss of operational control over critical infrastructure serving 10M+ citizens is a public safety emergency.
RSK-mna2ydsk | Untested DR site exploits assumed recovery capability causing failed failover during actual disaster event | Compliance | Business Continuity Manager | 3 | 5 | 15 | High | Open | DR site exists but hasn't been tested recently. When a real disaster hits, systems may be out of date, backups incomplete, or staff unsure of the procedure. | Likelihood 3 — untested DR is extremely common. Impact severe a failed failover during an actual disaster means extended downtime with no backup option.
RSK-mna2xmnv | Network failure exploits single point of failure in OT network causing loss of real-time SCADA monitoring and control | Availability | IT Operations | 3 | 4 | 12 | Medium | Open | OT network has no redundant path. A single device failure isolates operators from live systems. Can't monitor or adjust critical infrastructure in real time. | Likelihood 3 - network hardware failures happen and single points of failure are a known gap. Impact major loss of real-time monitoring creates immediate safety risk.