## Risk Register
EuroShop GmbH — GDPR Risk Register
Framework: GDPR ¦ Scope: Personal data processing for 3M+ EU customers across 27 member states
Risk ID | Risk Title | Category | Owner | Likelihood (1-5) | Impact (1-5) | Risk Score | Severity | Status | Description | Rationale
RSK-mn7pwtkf | External attacker exploits unencrypted customer database causing exposure of 3M+ EU customer PII | Data Protection | Data Protection Officer | 4 | 5 | 20 | Critical | Open | Customer database holds PII for 3M+ people. Weak encryption means one attacker who gets in walks away with everything. names, addresses, payment details. | Likelihood 4 because unencrypted databases are top attack targets. Impact severe triggers GDPR Article 33 notification and fines up to 4% of global turnover.
RSK-mn7pz3w1 | Data subject exploits absent DSAR procedure causing EuroShop to miss 30-day response obligation | Compliance | Data Protection Officer | 4 | 4 | 16 | High | Open | With 3M+ customers across 27 EU countries, DSARs come in regularly. No documented process means missed deadlines under GDPR Article 12. | Likelihood 4 volume makes DSARs inevitable. Impact major repeated missed deadlines trigger supervisory authority investigations.
RSK-mn7py1vh | EuroShop exploits missing lawful basis documentation causing unlawful processing of customer marketing data | Compliance | Data Protection Officer | 3 | 4 | 12 | Medium | Open | Marketing campaigns use customer data but lawful basis under GDPR Article 6 hasn't been documented. Processing is unlawful even with checkout consent. | Likelihood 3 common gap in fast-growing e-commerce. Impact major regulators can fine without a breach occurring.
RSK-mn7q03gf | Third-party processor exploits missing DPA causing uncontrolled personal data sharing outside GDPR boundaries | Vendor Risk | TPRM Lead | 3 | 4 | 12 | Medium | Open | Payment processor handles EU customer data without a signed DPA. Under GDPR Article 28, EuroShop is liable for how processors handle that data. | Likelihood 3 — DPAs missed during rapid vendor onboarding. Impact major — EuroShop remains liable for third-party mishandling of customer PII.
RSK-mn7q13ex | Insider threat exploits excessive employee access causing unauthorised viewing of customer personal data | Access Control | Security Lead | 3 | 4 | 12 | Medium | Open | 800 employees have access to customer systems beyond what their job requires. One misuse case triggers a GDPR investigation. | Likelihood 3 broad access is common in fast-scaling e-commerce. Impact major internal unauthorised access counts as personal data breach under GDPR Article 4.
RSK-mn7q22xa | EuroShop exploits lack of DPIA process causing high-risk data processing activities to proceed without assessment | Compliance | Data Protection Officer | 3 | 4 | 12 | Medium | Open | Large-scale processing of EU customer behavioural data requires a DPIA under GDPR Article 35. No process means high-risk activities go ahead without review. | Likelihood 3 DPIA requirements often overlooked when launching features. Impact major proceeding without a mandatory DPIA is itself a GDPR violation.