## Response Tasks
HealthTech Systems — Incident Response Task Tracker
Active response tasks supporting open incidents and IR program development
Task ID | Title | Priority | Status | Assignee | Due Date | Notes
TSK-mn8os8i9 | Develop and distribute IR playbook to all hospital security teams | Critical | In Progress | Security Operations Manager | 2026-03-11 | IR playbook covering ransomware, data breach, and phishing being drafted. Needs legal and CISO review before distribution to all 200+ hospital teams.
TSK-mn8ot1wl | Audit all active accounts and deprovision former employee credentials | Critical | In Progress | IT Operations | 2026-03-12 | Full account audit underway following Incident 2. Former staff accounts being deactivated immediately. IAM automation being configured to prevent recurrence.
TSK-mn8ou170 | Submit HHS breach notification for ransomware incident affecting 50,000 patients | Critical | In Progress | Security Operations Manager | 2026-03-12 | HIPAA 60 day clock started from Incident 1 discovery date. Legal reviewing notification draft. HHS and affected patients to be notified before deadline.
TSK-mn8oup53 | Schedule and conduct tabletop IR exercise with all hospital security teams | High | Not Started | SOC Manager | 2026-03-13 | Tabletop exercise design in planning. All IR team members required. Findings will feed into IR plan update.
TSK-mn8ov8dq | Verify offline backup restoration for all EHR systems post ransomware incident | Critical | Completed | DevOps Lead | 2026-03-14 | Full EHR restore from offline backup completed. Recovery within RTO. Backup gaps identified in 3 hospitals remediation in progress.