## Issues Log
FinSecure Banking — Compliance Gaps & Issues
Issue ID | Title | Category | Severity | Status | Owner | Due Date | Description
ISS-mn5ttkcl | PayCore SOC 2 Type II report not collected prior to integration approval | Compliance Issue | Critical | Open | TPRM Lead | 2026-03-09 | PayCore was onboarded without obtaining their SOC 2 Type II report. No independent proof their controls are working. Must be resolved before integration goes live.
ISS-mn5tuiy0 | No joint incident response procedure defined with PayCore for payment security events | Process Gap | High | Open | CISO | 2026-03-10 | No documented process between FinSecure and PayCore for handling a security incident. Both teams don't know who to call first. Gap needs closing before integration is live.
ISS-mn5tvjt2 | PayCore personnel access to FinSecure systems not reviewed or scoped to least privilege | Security Gap | High | In Progress | Security Lead | 2026-03-14 | PayCore staff have broader access than needed. Access review initiated but not complete. Risk of insider misuse remains open until review is done.