## Risk Register
FinSecure Banking — Vendor Risk Register
Frameworks: PCI DSS, SOC 2 ¦ Scope: PayCore payment processor integration
Risk ID | Risk Title | Category | Owner | Likelihood (1-5) | Impact (1-5) | Risk Score | Severity | Status | Description | Rationale
RSK-mn3fethw | External attacker exploits PayCore's weak network segmentation causing cardholder data breach in FinSecure's environment | Access Control | TPRM Lead | 4 | 5 | 20 | Critical | Open | PayCore connects directly to FinSecure's CDE. Poor segmentation means an attacker inside PayCore can reach our payment systems. | Likelihood 4 — third-party CDE access is a common attack path. Impact severe cardholder breach means PCI DSS violation and card scheme penalties.
RSK-mn3fg9yo | PayCore exploits absence of SOC 2 Type II attestation causing unverified security posture in payment integration | Compliance | TPRM Lead | 3 | 4 | 12 | Medium | Open | PayCore's SOC 2 Type II report hasn't been collected. We have no independent proof their controls are working. | Likelihood 3 — vendors let attestations lapse or share outdated reports. Impact major — no verification means FinSecure is exposed during OCC regulatory review.
RSK-mn3fid1s | Insider threat exploits excessive PayCore access privileges causing unauthorised transaction data exposure | Access Control | Security Lead | 3 | 4 | 12 | Medium | Open | PayCore staff may have more access than needed. A rogue or compromised account can misuse transaction data sitting in our environment. | Likelihood 3 — access scope hasn't been reviewed yet. Impact major — insider misuse of payment data directly violates PCI DSS Requirement 7.
RSK-mn3fjo0g | PayCore exploits lack of incident response coordination causing delayed breach containment affecting FinSecure customers | Compliance | CISO | 3 | 4 | 12 | Medium | Open | No process defined for how PayCore and FinSecure handle a security incident together. Delayed notification means slower containment on our side. | Likelihood 3 — vendor IR coordination is rarely defined upfront. Impact major — delayed breach notification violates PCI DSS Req 12.10 and OCC requirements.